## Project
id | name | start_date | budget | baseline_qty
1 | Building A | 2026-01-01 | 5000000 | 100

## Task
id | project_id | name | planned_duration | planned_cost
1 | 1 | Excavation | 5 | 300000
2 | 1 | Foundation | 10 | 800000
3 | 1 | Structure | 25 | 2500000
4 | 1 | Masonry | 20 | 1400000

## Resource
id | type | name | cost_per_unit
1 | HR | Worker | 500
2 | Equipment | Excavator | 10000
3 | Material | Concrete | 1200
4 | Material | Brick | 800

## DailyReport
id | project_id | task_id | date | progress_percent | actual_cost
1 | 1 | 1 | 2026-01-01 | 10 | 50000
2 | 1 | 1 | 2026-01-02 | 25 | 120000
3 | 1 | 1 | 2026-01-03 | 40 | 200000
4 | 1 | 2 | 2026-01-06 | 10 | 100000
5 | 1 | 2 | 2026-01-07 | 20 | 250000

## ResourceUsage
id | daily_report_id | resource_id | amount
1 | 1 | 1 | 5
2 | 1 | 2 | 1
3 | 2 | 1 | 8
4 | 2 | 2 | 1
5 | 3 | 1 | 10
6 | 4 | 1 | 6
7 | 4 | 3 | 20
8 | 5 | 1 | 7
9 | 5 | 3 | 30